## Sheet1
Project Log
Week no. | Start | End | Work Completed
1 | 2017-11-26 | 2017-12-04 | Project Selection and Abstract Creation
2 | 2017-12-04 | 2017-12-11 | Dataset Selection and Architecture Selection
3 | 2017-12-11 | 2017-12-18 | Researched Sampling and Data Augmentation stratergies to increase the accuracy of the models in face of criterions such as occlusion and illumination diffrence
4 | 2017-12-18 | 2017-12-26 | Downloading and performing basic Exploratory Data Analysis on Lone Faces in Wild Dataset (LFW - Face Recognition) and Wider Dataset(Face Detection)
5 | 2017-12-26 | 2018-01-01 | Winter Vacation
6 | 2018-01-01 | 2018-01-08 | Creating a uniform environment for easier workflow in GitHub
7 | 2018-01-08 | 2018-01-15 | Tried Nvidia-Docker for GPU based containers (Too many issues porting it to other systems, hence dropped the idea)
8 | 2018-01-15 | 2018-01-22 | Trained the Face Recognition model created by Jugat (since my laptop had a GPU), created code for inferencing (for Face Recognition Model) as well as intergreating it with video capture and face detection code created by Adithya